## Slide 1: EVENT PLANNING:
Check List

## Slide 2
Below is a link to the LSU web site where you will
find the events Jot Form
https://lsu.co.uk/forms
ALL events MUST be booked using this form.
Due to COVID-19 LSU have the right to cancel or
alter restrictions on all events.
All booked events will be regularly reviewed to ensure
they meet up to date COVID-19 regulations.

## Slide 3: Planning your event
The next few slides are checklists designed to help you plan your event in stages
These are designed to edit or print out
We also strongly advise you have 2 plans for the event;
    Plan A – Your Event Plan
    Plan B – Your COVID Event Plan

## Slide 4: Step 1 - Initial event planning
What are your event goals/ objectives | NB: How are you going to measure them? Use SMART targets – see slides 5/6 | 
Fill in the Online Jot Form and submit | NB: Check room/ speakers and equipment availability | 
Make an Event Budget Sheet | NB: Excel is a great tool for this. See an example of a budget sheet – slide 7 | 
Do you need any funding? | NB: Look out for the Finding Funding resources | 
Create an Event Committee | NB: try and match the tasks with the persons skills | 
Use a time line to plan your publicity/ social media marketing | NB: Plan posts to go out before/during and after the event. | 
Brand Your Event | NB: Don’t forget to get this approved through marketing@lsu.co.uk | 
Confirm speakers/ presenters/entertainers | NB: Don’t forget to fill in an external speaker form (on the Jot Form) | 
Arrange regular meetings with your event committee | NB: Keep everyone up to day with a group chat. Remember to delegate – plan when each step needs to be completed | 
Be COVID-19 Prepared | NB: Create a 2nd plan that will fit with any shutdown regulations | 

## Slide 5
S . M . A . R . T
Specific
Measurable
Attainable
Realistic
Time
Be clear on your goal
What do you want to accomplish?
Why is it important?
How much?
How many?
When is it accomplished?
When is it being reviewed?
Is the goal realistic & within reach?
Can you commit to the goal?
Does it fit within your time & resources?
Is the goal achievable?
What do you need to achieve the goal?
Has it been done successfully before?
Define the start & finish dates.
What is the deadline?
When do you want to achieve the goal by?

## Slide 6
S . M . A . R . T
Specific
Measurable
Attainable
Realistic
Time

## Slide 7: a budget sheet
ITEM | MONEY IN | MONEY OUT
Section budget for event | £100 | 
Sponsorship from John’s recruitment | £200 | 
Ticket sales ( estimate before/update after) | £100 | 
All tech – lighting/music |  | £200
Decoration |  | £100
Printed tickets |  | £50
TOTAL (including VAT) | £400 | £350
These need to be the same
(or money in be higher = profit)
Check all items purchased
Include VAT

## Slide 8: STEP 2 – 1 Month before the event
Organise an update meeting with your event committee | NB: Don’t forget to praise your committee if they have done a good job. As well as dealing with conflict – side 9 | 
Speaker/ presenter liaison | NB: Finalise speech topics and ask them to share the event with their networks Are you filming the event? Do you need permission? | 
Budgets/Costings | NB: Make sure all budget plans are up to date. Has funding been found? What other ways can you find budget? Request logos form sponsors in high res | 
Confirm venue details | NB: check if you need any extra staff to work the event. | 
Ticket Sales | NB: Is this a ticketed event? If so, when do tickets go on sale? Are you offering an early bird discount? What happens if the event is cancelled? | 
Publicity Plan | NB: do you need to have a link to the event on your web page? What posts do you have scheduled? | 

## Slide 9
5 Steps to Conflict Resolution
Identify the source of the conflict
  What has caused the conflict – ask the question and listen without judgment or comment.
Looking beyond the incident
  When did the conflict start? Was it an previous comment or incident?
Request Solutions
  Be the mediator between parties. Listen and ask how could this be resolved.
Identify Solutions both disputants can support
  Look for the most acceptable course of action that benefits both parties and the organisation.
Agreement
  Once the parties have agreed a resolution, discuss action plans on how this can be prevented in the future.

## Slide 10: Step 3 – 1 week before your event
Check all details of your booking are covered | NB: arrange a meeting with venue /marketing /media | 
Arrange update meeting with event committee | NB: check they are all up to date with jobs have delegated. Provide help or support if required Go through plans for the day of the event. | 
Update and review the publicity plans | NB: are you getting the good uptake on social media? If not, what can you change? Are all the committee liking and sharing? | 
Ticket Sales | NB: review ticket sales and how you could boost this ahead of the event? Have you booked contactless payment machine from finance? | 
Risk Assessment | NB: review your risk assessment with the appropriate LSU staff member | 
Collecting Data | NB: Are you collecting student data – who attends/ adding students to a news letter? Make sure you adhere to GDPR - online training is available. | 
Speakers/Presenters | NB: Check all travel details and details of where you are meeting them are in place. | 
Make a check list | NB: be prepared with a check list for the day of the event to make sure everything is in place | 

## Slide 11: Step 4 – the day of the event
Take a few deep breaths | You have got this! | 
Risk Assessment | NB: this needs to be checked and signed off before the event. Make sure everyone knows the fire procedure. | 
Media and Tech | NB: run through all tech including videos/links/power points/speakers/ mics and any filming equipment | 
Timings | NB: be clear on timings for the event and stick to them. | 
Speakers and presenters | NB: who is going to met and greet? Offer your guests refreshments if required. | 
Publicity | Who is scheduling posts before and during the event? Do you have a hashtag your audience and guests can use? | 
Setting up | NB: give yourself enough time to set up comfortably. Are your committee on hand to help? | 
Collecting data/tickets/ entrance fee | NB: do you have a hand scanner to collect B Numbers? Who is collecting tickets/money? | 

## Slide 12: Step 5 – after the event – Well done, you did it!
Clearing up after the event | Make sure you have a team to help pack up and clear away. NB: Check that all equipment has been returned. Money has been banked and media downloaded. | 
Publicity | Post pictures, videos and feedback from the event. Tagging sponsors or speaker Write an article about the event to be posted on the LSU or LU webpages or newsletters. | 
Say Thank You | Send thank you letters to all speakers/sponsors AND your event committee. NB: your sponsors will want to know how the event went, what impact it made some photos and feedback. | 
Finances | Update your budget sheet – make sure you have all expenses covered. | 
Lessons Learnt | If you are going to run the event again in the future you might want to arrange a post event meeting to go through what went well and what could be improved. You may want to put a survey out to attendees. | 

## Slide 13: any questions? Contact your section chair or relevant member of staff for more help